## Dec
Aung Kyaw Min Htet (Embedded Developer) 2024 December Daily Report Digital Engineering Tech Ltd.
Date | No | Task Decription | Assigned by | Task Status | Next Steps | Bottleneck
2.12.2024 | 1 | POS Server update YE Kyaw San Station |  | completed
| 2 | RedStar Dongle Firmware Documentation Generate with Doxygen | SrTHK | completed
| 3 | POS Toch Controller Error check from Khathit Kan Station |  | completed
| 4 | Manage POS Dongle setup and installation at AungPam Station | GM | completed
| 5 | Touch Controller Firmware Documentation Generate with Doxygen | SrTHK | completed
3.12.2024 | 1 | collect and transfer Documentation to SrTHK | CEO | completed
| 2 | prepre for prime dongle firmware to Doxygen Document Format | SrTHK | completed
| 3 | prepre for Tatsuno Dongle firmware to Doxygen Document Format | SrTHK | completed
| 4 | Manage POS Dongle setup and installation at AungPam Station | GM | completed
| 5 | meeting with SrTHK | CEO | completed
| 6 | ATG find and test with protocol and CRC function |  | processing |  | Find and testing CRC converter function
4.12.2024 | 1 | ATG find and test with protocol |  | completed
| 2 | Manage POS Dongle setup and installation at AungPam Station | GM | completed
| 3 | meeting with CEO and rnd team | CEO | completed
| 4 | Solved WiFi Router error for Naung Voe Nging Station | SrFS | completed
5.12.2024 | 1 | Checking Totalizer different from Naung Voe Nging Station | SrFS | completed
| 2 | Orange pi preparation to transfer for SrFS | CEO | completed
| 3 | Prepare V4 Dongle to update for Ye Station |  | completed
| 4 | Checking find and search error in Cloud |  | completed
6.12.2024 | 1 | Checking how to send data from two esp UART from OJT |  | completed
| 2 | Prepare POS installation for Linn Station | GM | completed
| 3 | Prepare one nozzle Red Star firmware to test in Tatkon Station | GM | processing
| 4 | Explain and test read data from WaterFlow HMI UI for assign OJT |  | completed
7.12.2024 | 1 | travelled to Linn Station at Tatkon | GM | completed
| 2 | setup Touch controller, U913 converter, POS Dongle and power supply | GM | completed
3
8.12.2024 | 1 | We setup Server and Touch Controller | GM | co
| 2 | Explain how to use Touch Controller and POS software | GM | completed
| 3 | Checking Selling with PoS Touch Controller | GM | completed
| 4 | We signed installation finished form with station owner | GM | completed
9.12.2024 | 1 | Testing One Nozzle Firmware at Tatkon KS Station | GM | completed
| 2 | Checking and Testing tank data from SrFS at KS Tatkon | SrFS | completed
| 3 | test and solved preset amount error at Linn Station |  | completed
| 4 | Solved Touch Controller Touch Error |  | completed
10.12.2024 | 1 | testing and update Firmware appro function |  | completed
| 2 | Checking voucher and data |  | completed
| 3 | Change Touch controller Screen error with new one |  | completed
| 4 | Find UART communication Error with firmware |  | completed
11.12.2024 | 1 | Solved U913 converter Error and change with new device |  | completed
| 2 | We come back to main office | GM | completed
| 3 | Office Gathering metting | CEO | completed
| 4 | We check installation tools and extra equipment |  | completed
12.12.2024 | 1 | We travelled to Mandalay with GM, SE | GM | completed
| 2 | We survey Fuel Station | GM | completed
3
4
13.12.2024. | 1 | testing final data, live data convert and send data | CEO | completed
| 2 | Testing gilbarco firmware | CEO | processing
14.12.2024 | 1 | Prepare one nozzle Red Star firmware for MinBu and Kathitkan Station | GM | completed
| 2 | Testing gilbarco firmware | CEO | processing |  | To test Four nozzle, waiting for two level pump setting code from Sein Maung
15.12.2024 | 1 | testing Send live data from mqtt |  | completed
| 2 | solve Uart noise error |  | completed
16.12.2024 | 1 | We setup power supply, POS Dongle, U913 converter at AKW Station |  | completed
2
17.12.2024 | 1 | Testing 2nozzle gilbarco firmware at Sein Station |  | processing
| 2 | testing livedata, transaction data, final data, sending pump permit |  | completed
| 3 | Meeting with SrTHK | CEO | completed
| 4 | Test address setup and pos mode for 4nozzle dispener |  | completed
18.12.2024 | 1 | We setup Wifi Router and Sever at AKW Station |  | completed
| 2 | prepare Touch Controller firmware for internal eeprom Version |  | completed
| 3 | POS Server Service installation Setup |  | completed
| 4 | Test and check Dongle and dispenser connection at AKW station |  | completed
19.12.2024 | 1 | Test pump appro function gibarco firmware |  | completed
| 2 | solved and test firmware error |  | completed
| 3 | test and selling using POS system with gibarco Dispenser |  | completed
| 4 | We setup power supply and dongle at Sein Station |  | completed
20.12.2024 | 1 | test and solved Four nozzle gilbarco firmware |  | processing
| 2 | power supply and dongle setup 4nozzle dispenser |  | completed
| 3 | Setup WiFi Router and Server |  | completed
21.12.2024 | 1 | Training for selling POS software at AKW station |  | completed
| 2 | Four Nozzle Gilbarco firmware testing |  | processing
22.12.2024 | 1 | training and watch selling with POS software at AKW station |  | completed
| 2 | Installation finished sign with owner |  | completed
| 3 | Solved and update 4nozzle Gilbarco firmware |  | completed
23.12.2024 |  | POS usage Training at Sein Station | GM | completed
|  | Bought new computer for AKW Station and POS Software account setup | GM | completed
|  | Training Handheld POS usage at AKW Station | GM | completed
|  | Installation finished sign with Sein Station owner | GM | completed
24.12.2024 |  | We are back to the naypyitaw office at 8:30 AM | GM | completed
|  | We arrived office at 2:30 PM | GM | completed
|  | Installation finished form Dedicated to Finance Department |  | completed
26.12.2024 |  | Find and solved error Touch Controller primary board |  | completed
|  | explain and solve mqtt error for OJT |  | completed
|  | Red Star firmware prepare with documentation | CEO | completed
27.12.2024 |  | Pi server image flash for OJT |  | completed
|  | Testing Tokico Dispenser at Station | GM | completed
|  | Office Donation | HR | completed
28.12.2024 |  | Check and solved error at Pindaya Station | GM | completed
|  | prepare firmware 2 decimal for final data |  | completed
|  | Red Star firmware prepare with documentation | CEO | processing
31.12.2024
မှတ်ချက်။ Bottleneck နေရာတွင် Stuck ဖြစ်နေသည့် Problem များ ရေးသားရန်

## Jan
Daw / U…........(…..Position…......) 2024 December Daily Report Digital Engineering Tech Ltd.
Date | No | Task Decription | Assigned by | Task Status | Next Steps | Bottleneck
1.1.2025 | 1
2
3
2.1.2025 | 1
2
3
4
3.1.2025 | 1
2
4.12.2024 | 1
2
3
4
5
မှတ်ချက်။ Bottleneck နေရာတွင် Stuck ဖြစ်နေသည့် Problem များ ရေးသားရန်