## 23~28 Weekly
Aung Kyaw Min Htet (Embedded Developer) 23~28 December Weekly Report Digital Engineering Tech Ltd.
No. | Task Decription | Assigned by | Task Status | Next Steps | Bottleneck
1 | POS usage Training at Sein Station | GM | completed
2 | Bought new computer for AKW Station and POS Software account setup | GM | completed
3 | Training Handheld POS usage at AKW Station | GM | completed
4 | Installation finished sign with Sein Station owner | GM | completed
5 | We are back to the naypyitaw office at 8:30 AM | GM | completed
6 | We arrived office at 2:30 PM | GM | completed
7 | Installation finished form Dedicated to Finance Department | GM | completed
8 | Find and solved error Touch Controller primary board |  | completed
9 | explain and solve mqtt error for OJT |  | completed
10 | Red Star firmware prepare with documentation | CEO | completed
11 | Pi server image flash for OJT |  | completed
12 | Testing Tokico Dispenser at Station | GM | completed
13 | Office Donation | HR | completed
14 | Check and solved error at Pindaya Station | GM | completed
15 | prepare firmware 2 decimal for final data |  | completed
16 | Red Star firmware prepare with documentation | CEO | processing

## 16~22 Weekly
Aung Kyaw Min Htet (Embedded Developer) 16~22 December Weekly Report Digital Engineering Tech Ltd.
No. | Task Decription | Assigned by | Task Status | Next Steps | Bottleneck
1 | We setup power supply, POS Dongle, U913 converter at AKW Station |  | completed
2 | Testing 2nozzle gilbarco firmware at Sein Station |  | completed
3 | testing livedata, transaction data, final data, sending pump permit |  | completed
4 | Meeting with SrTHK | CEO | completed
5 | Test address setup and pos mode for 4nozzle dispener |  | completed
6 | We setup Wifi Router and Sever at AKW Station |  | completed
7 | prepare Touch Controller firmware for internal eeprom Version |  | completed
8 | POS Server Service installation Setup |  | completed
9 | Test and check Dongle and dispenser connection at AKW station |  | completed
10 | Test pump appro function gibarco firmware |  | completed
11 | solved and test firmware error |  | completed
12 | test and selling using POS system with gibarco Dispenser |  | completed
13 | We setup power supply and dongle at Sein Station |  | completed
14 | test and solved Four nozzle gilbarco firmware |  | completed
15 | power supply and dongle setup 4nozzle dispenser |  | completed
16 | Setup WiFi Router and Server |  | completed
17 | Training for selling POS software at AKW station |  | completed
18 | Four Nozzle Gilbarco firmware testing |  | completed
19 | training and watch selling with POS software at AKW station |  | completed
20 | Installation finished sign with owner |  | completed
21 | Solved and update 4nozzle Gilbarco firmware |  | completed |  | To test Four nozzle, waiting for two level pump setting code from Sein Maung

## 9~15 Weekly
Aung Kyaw Min Htet (Embedded Developer) 9~15 December Weekly Report Digital Engineering Tech Ltd.
No. | Task Decription | Assigned by | Task Status | Next Steps | Bottleneck
1 | Testing One Nozzle Firmware at Tatkon KS Station | GM | completed
2 | Checking and Testing tank data from SrFS at KS Tatkon | SrFS | completed
3 | test and solved preset amount error at Linn Station |  | completed
4 | Solved Touch Controller Touch Error |  | completed
5 | testing and update Firmware appro function |  | completed
6 | Checking voucher and data |  | completed
7 | Change Touch controller Screen error with new one |  | completed
8 | Find UART communication Error with firmware |  | completed
9 | Solved U913 converter Error and change with new device |  | completed
10 | We come back to main office | GM | completed
11 | Office Gathering metting | CEO | completed
12 | We check installation tools and extra equipment |  | completed
13 | We travelled to Mandalay with GM, SE | GM | completed
14 | We survey Fuel Station | GM | completed
15 | testing final data, live data convert and send data |  | completed
16 | Prepare one nozzle Red Star firmware for MinBu and Kathitkan Station | GM | completed
17 | Testing gilbarco firmware | CEO | completed |  | To test Four nozzle, waiting for two level pump setting code from Sein Maung

## 1~8 Weekly
Aung Kyaw Min Htet (Embedded Developer) 1~8 December Weekly Report Digital Engineering Tech Ltd.
စဉ် | အကြောင်းအရာ | ညွှန်ကြားသူ | လုပ်ငန်းပြီးမြောက်မှုအခြေအနေ | ဆက်လက်လုပ်ဆောင်မည့်အနေအထား | မှတ်ချက်
1 | POS Server update YE Kyaw San Station |  | completed
2 | RedStar Dongle Firmware Documentation Generate with Doxygen | STHK | completed
3 | Touch Controller Firmware Documentation Generate with Doxygen | STHK | completed
4 | POS Toch Controller Error check from Khathit Kan Station |  | completed
5 | Manage POS Dongle setup and installation at AungPam Station | GM | completed
6 | collect and transfer Documentation to SrTHK | CEO | completed
7 | prepre for prime dongle firmware to Doxygen Document Format | STHK | completed
8 | prepre for Tatsuno Dongle firmware to Doxygen Document Format | STHK | completed
9 | meeting with SrTHK | CEO | completed
10 | meeting with CEO and rnd team | CEO | completed
11 | Solved WiFi Router error for Naung Voe Nging Station |  | completed
12 | Checking Totalizer different from Naung Voe Nging Station |  | completed
13 | Orange pi preparation to transfer for SrFS | CEO | completed
14 | Prepare V4 Dongle to update for Ye Station |  | completed
15 | Checking find and search error in Cloud |  | completed
16 | Checking how to send data from two esp UART from OJT |  | completed
17 | Prepare POS installation for Linn Station | GM | completed
18 | Prepare one nozzle Red Star firmware to test in Tatkon Station |  | completed
19 | Explain and test read data from WaterFlow HMI UI for assign OJT |  | completed
20 | travelled to Linn Station at Tatkon | GM | completed
21 | setup Touch controller, U913 converter, POS Dongle and power supply |  | completed
22 | We setup Server and Touch Controller |  | completed
23 | Explain how to use Touch Controller and POS softeare |  | completed
24 | Checking Selling with PoS Touch Controller |  | completed
25 | We signed installation finished form with station owner |  | completed
26
27
28