## October
U Aung Kyaw Min Htet (Embedded Developer) November Daily Report Digital Engineering Tech Ltd.
ရက်စွဲ | စဉ် | အကြောင်းအရာ | ညွှန်ကြားသူ | လုပ်ငန်းပြီးမြောက်မှုအခြေအနေ | ဆက်လက်လုပ်ဆောင်မည့်အနေအထား | မှတ်ချက်
2.11.2024 | 1 | Touch contoller Error handling Documentation | CEO | processing
| 2 | ATG Documentaion | CTO | processing
4.11.2024 | 1 | OJT Arduino Preparation | CTO | completed
| 2 | Touch contoller Error handling Documentation | CEO | processing
5.11.2024 | 1 | Explain to OJT process and usage of delay 4 channel module | CTO | completed
| 2 | Solved Touch Controller power off at Kathit kan station | CTO | completed
6.11.2024 | 1 | Explain to OJT linux command and Rasberry pi ssh usage | CTO | completed
| 2 | Prepare Tools and Equipments for testing gilbarco dispenser | GM | completed
| 3 | We travelled to mandalay at 9 PM | GM | completed
7.11.2024 | 1 | We arrived at Sein Fuel Stating at 8 AM | GM | completed
| 2 | Find UART Communication from Dispenser mother board and found RS-485 , Two -wire communication | CTO | completed
| 3 | Find and test pump address change from dispenser | CTO | completed
| 4 | Find and test pos mode change from dispenser | CTO | completed
8.11.2024 | 1 | We meet with officer Daw ThaeHninSoe at Petrol main office (Mandalay). | GM | completed
| 2 | We survey Seven Start fuel station at Ohm Chaw. | GM | completed
3
9.11.2024 | 1 | find and testing RS-485 communication with gilbarco mother borad | CTO | completed
| 2 | After getting communication, we test with protocol | CTO | processing
10.11.2024 | 1 | We Survey ThaZinPam fuel Station and SeinSiAung Fuel Station | GM | completed
| 2 | Find and test with gilbarco protocol | CTO | processing
11.11.2024 | 1 | Find and testing appro protocol | CEO | completed
| 2 | we convert from sending last dispenser data. | CEO | completed
| 3 | Find and test preset protocol | CEO | processing
12.11.2024 | 1 | Find and testing preset protocol | CEO | processing
| 2 | Find and testing price change protocol | CEO | processing
13.11.2024 | 1 | Find and testing price change protocol | CEO | processing
2
14.11.2024 | 1 | Firmware testing with Dongle | CEO | processing
| 2 |  | CEO | processing
16.11.2024 | 1 | Pump appro and normal state firmware testing with Dongle | CEO | processing
| 2 | We travelled to naypyitaw at 3:30 PM | GM | completed
| 3 | We arrived at naypyitaw around 9 PM | GM | completed
18.11.2024 | 1 | Explained the MQTT and Server How it works to OJT |  | completed
| 2 | Explain how to do and work HMI Display software setup | CEO | completed
20.11.2024 | 1 | We solved Dispenser gun Sensor error at MinBu Station |  | completed
| 2 | Setup HMI Display image flash using DGUS Software |  | completed
21.11.2024 | 1 | We travelled Tatkon Station for ATG installation | GM | completed
| 2 | We survey Sein ThaZin Station | GM | completed
| 3 | we setup ATG Api Route and testing with POS Server | CTO | completed
22.11.2024 | 1 | We bind ATG static ip address to banana pi Server | CEO | processing
| 2 | We survey Linn Station at tatkon | GM | completed
| 3 | We survey Shwe Pha lar Station at tatkon | GM | completed
| 4 | We update Handheld POS App software update | GM | completed
5
23.11.2024 | 1 | Check and solve error for OJT project code | CEO | completed
| 2 | Setup and solved Error ATG data to Cloud Tatkon Station | CEO | completed
| 3 | testing Tokico Dispenser | CEO | processing
26.11.2024 | 1 | Prepare banapi R3 to transport at yangon for testing static ip address | CEO | completed
| 2 | Tokico dispenser testing | CEO | processing
27.11.2024 | 1 | Tokico dispenser testing | CEO | processing |  | Memory Error occur again
| 2 | Find and Solved Touch controller error at kathitkan station
မှတ်ချက်။ အကြောင်းအရာ၊ ညွှန်ကြားသူ၊ လုပ်ငန်းပြီးမြောက်မှုအခြေအနေတို့အား မဖြစ်မနေ ရေးသားဖြည့်စွက်ရမည်ဖြစ်ပြီး ဆက်လက်လုပ်ဆောင်မည့်အနေအထားနှင့် မှတ်ချက် တို့အား လိုအပ်ပါက ရေးသားဖြည့်စွက်ရန်ဖြစ်ပါသည်။