## 1~6 Weekly
Aung Kyaw Min Htet (Embedded Developer) 1~6 October Weekly Report Digital Engineering Tech Ltd.
စဉ် | အကြောင်းအရာ | ညွှန်ကြားသူ | လုပ်ငန်းပြီးမြောက်မှုအခြေအနေ | ဆက်လက်လုပ်ဆောင်မည့်အနေအထား | မှတ်ချက်
1 | We installed POS Server and Touch Controller at pindaya Station | CTO | completed
2 | We setup user and cloud account | CTO | completed
3 | We Setup initial data Server and Touch controller | CTO | completed
4 | We checked data from mqtt, server log and dongle | CTO | completed
5 | We solve UART error and hardware error | CTO | completed
6 | Solved Wifi Router reset error and Wifi Configure setup for Yedashe Station | CTO | completed
7 | We explained usage of POS Software and rule of usage. | CTO | completed
8 | After finished installation, We sign the dedication form with manager. | CTO | completed
9 | We returned from aungban to the office at 2PM. | CTO | completed
10 | We arrived to naypyitaw around 9PM. | CTO | completed
11 | solved Serve error at Yedashe Station | CTO | completed
12 | find and solve Touch controller error | CTO | completed

## 7~13 Weekly
Aung Kyaw Min Htet (Embedded Developer) 7~13 October Weekly Report Digital Engineering Tech Ltd.
စဉ် | အကြောင်းအရာ | ညွှန်ကြားသူ | လုပ်ငန်းပြီးမြောက်မှုအခြေအနေ | ဆက်လက်လုပ်ဆောင်မည့်အနေအထား | မှတ်ချက်
1 | Touch controller error find, upload firmware and testing | CTO | completed
2 | Prepare Touch controller 1 set, Dongle and pi server to test for Ma Zin Mar Kyaw | CEO | completed
3 | Touch controller error find, upload firmware send it back to the kathitkan station | CTO | completed
4 | We prepare installation tools, POS package for PyawBywe Station Installation and testing | CTO | completed
5 | Touch controller error find sending form Ye Station | CTO | completed
6 | Prepare Touch controller for Natogyi Station | GM | completed
7 | We prepare POS package for Kyine Tone Station Installation | GM | completed
8 | We prepare Touch controller 3set for Natogyi Station | GM | completed
9 | we send back tokico test dispenser for change memory backup battery to naypitaw Suzuki showroom | SE | completed
10 | HMI Doucumentaion preparation | CEO | processing
11 | Testing bpi R3 |  | processing
12 | HMI Firmware update and testing |  | processing
13
14
15
16
17
18
19
20
21
22

## 21~27 Weekly
Aung Kyaw Min Htet (Embedded Developer) 21~27 October Weekly Report Digital Engineering Tech Ltd.
စဉ် | အကြောင်းအရာ | ညွှန်ကြားသူ | လုပ်ငန်းပြီးမြောက်မှုအခြေအနေ | ဆက်လက်လုပ်ဆောင်မည့်အနေအထား | မှတ်ချက်
1 | HMI dongle firmware update and explain each function with comment | CTO | completed
2 | Solve WiFi Router auto reset error in Shwe Sin SatKyar | CTO | completed
3 | Touch Controller prepare with update arduino ide | CTO | completed
4 | ATG Testing , find and connect pin with Sensor | CTO | completed
5 | U-913 converter test | CTO | completed
6 | ATG Testing with Dongle V2 | CTO | processing
7 | Led board error and solve | CTO | completed
8 | Touch Controller Documentaion | CEO | processing
13
14
15
16
17
18
19
20
21
22

## 28~2 Weekly
Aung Kyaw Min Htet (Embedded Developer) 28~2 October Weekly Report Digital Engineering Tech Ltd.
စဉ် | အကြောင်းအရာ | ညွှန်ကြားသူ | လုပ်ငန်းပြီးမြောက်မှုအခြေအနေ | ဆက်လက်လုပ်ဆောင်မည့်အနေအထား | မှတ်ချက်
1 | ATG Testing with Dongle V2 to get all data | CTO | completed
2 | ESP Web server api testing | CTO | completed
3 | Error Handling and Troubleshooting Touch controller | CTO | processing
4 | ATG Firmware with ESP Web sever api | CTO | completed
5 | Touch contoller Error handling Detail Documentation | CEO | processing
6 | ATG Testing with Dongle V2 | CTO | processing
7 | ATG Documentaion | CTO | processing
13
14
15
16
17
18
19
20
21
22