## October
Aung Kyaw Min Htet(Embedded Developer) October Daily Report Digital Engineering Tech Ltd.
ရက်စွဲ | စဉ် | အကြောင်းအရာ | ညွှန်ကြားသူ | လုပ်ငန်းပြီးမြောက်မှုအခြေအနေ | ဆက်လက်လုပ်ဆောင်မည့်အနေအထား | မှတ်ချက်
1.10.2024 | 1 | We installed POS Server and Touch Controller at pindaya Station | CTO | completed
| 2 | We setup user and cloud account | CTO | completed
| 3 | We Setup initial data Server and Touch controller | CTO | completed
2.10.2024 | 1 | We checked data from mqtt, server log and dongle | CTO | processing
| 2 | We solve UART error and hardware error | CTO | processing
3.10.2024 | 1 | We checked data from mqtt, server log and dongle | CTO | completed
| 2 | We solved UART error and hardware error | CTO | completed
| 3 | Solved Wifi Router reset error and Wifi Configure setup for Yedashe Station | CTO | completed
| 4 | We explained usage of POS Software and rule of usage. | CTO | completed
4.10.2024 | 1 | After finished installation, We sign the dedication form with manager. | CTO | completed
| 2 | We returned from aungban to the office at 2PM. | CTO | completed
| 3 | We arrived to naypyitaw around 9PM. | CTO | completed
5.10.2024 | 1 | solved Serve error at Yedashe Station | CTO | completed
| 2 | find and solve Touch controller error | CTO | processing
| 3 | Prepare Touch controller documentaion | CTO | processing
7.10.2024 | 1 | Touch controller error find, upload firmware and testing | CTO | processing
| 2 | Prepare Touch controller 1 set, Dongle and pi server to test for Ma Zin Mar Kyaw | CTO | processing
8.10.2024 | 1 | Touch controller error find, upload firmware send it back to the kathitkan station | CTO | completed
| 2 | We prepare installation tools, POS package for PyawBywe Station Installation and testing | CTO | completed
| 3 | Testing equipments send to the Ma Zin Mar Kyaw | GM | completed
9.10.2024 | 1 | Touch controller error find sending form Ye Station | CTO | completed
| 2 | Prepare Touch controller for Natogyi Station | GM | completed
10.10.2024 | 1 | change Touch screen error with new one that sent it back to the Ye Station | CEO | completed
| 2 | update HMI Firmware | CTO | processing
| 3 | We prepare POS package for Kyine Tone Station Installation | GM | completed
11.10.2024 | 1 | We prepare Touch controller 3set for Natogyi Station | GM | completed
| 2 | we send back tokico test dispenser for change memory backup battery to naypitaw Suzuki showroom | SE | completed
| 3 | Testing bpi R3 |  | processing
12.10.2024 | 1 | HMI Doucumentaion preparation | CEO | processing
| 2 | HMI dongle firmware update |  | processing
| 3 | Testing bpi R3 |  | processing
21.10.2024 | 1 | Touch Controller Documentaion | CEO | processing
| 2 | HMI dongle firmware update and explain each function with comment | CTO | processing
22.10.2024 | 1 | Solve WiFi Router auto reset error in Shwe Sin SatKyar | CTO | completed
| 2 | Touch Controller prepare with update arduino ide |  | completed
| 3 | ATG Testing | CTO | processing
| 4 | Touch Controller Documentaion | CEO | processing
23.10.2024 | 1 | Touch Controller Documentaion | CEO | processing
| 2 | U-913 converter test | CTO | processing
24.10.2024 | 1 | U-913 converter test | CTO | completed
| 2 | ATG Testing | CTO | processing
25.10.2024 | 1 | ATG Testing with Dongle V2 | CTO | processing
| 2 | Led board error and solve | CTO | completed
26.10.2024 | 1 | Touch Controller Documentaion | CEO | processing
| 2 | ATG Testing with Dongle V2 | CTO | processing
28.10.2024 | 1 | ATG Testing with Dongle V2 to get all data | CTO | processing
| 2 | ESP Web server api testing | CTO | processing
29.10.2024 | 1 | ATG Firmware with ESP Web sever api | CTO | processing
| 2 | Error Handling and Troubleshooting Touch controller | CEO | processing
30.10.2024 | 1 | ATG Firmware with ESP Web sever api | CTO | processing
2
31.10.2024 | 1 | ATG Firmware with ESP Web sever api | CTO | completed